## schedule
scheduled for FV automated ters :- |  |  |  | Schedule for ISST weekly automated ters :- |  |  | power model | cec name | hmc | vios name | owner | responsibility
keep cec firmware level & vios level updated. Resolve issues if any arises at cec or vios level
iteration | start date | end date |  | iteration | start date | end date
ctc-2w-01 | 2020-10-19 | 2020-10-30 |  | ctc01 | 2020-10-19 | 2020-10-23
ctc-2w-02 | 2020-11-02 | 2020-11-13 |  | ctc02 | 2020-10-26 | 2020-10-30
ctc-2w-03 | 2020-11-16 | 2020-11-27 |  | ctc03 | 2020-11-02 | 2020-11-06
ctc-2w-04 | 2020-11-30 | 2020-12-11 |  | ctc04 | 2020-11-09 | 2020-11-13
ctc-2w-05 | 2020-12-14 | 2020-12-25 |  | ctc05 | 2020-11-16 | 2020-11-20 | cec's for nov sp
ctc-2w-06 | 2020-12-28 | 2020-01-08 |  | ctc06 | 2020-11-23 | 2020-11-27
ctc-2w-07 | 2020-01-11 | 2020-01-22 |  | ctc07 | 2020-11-30 | 2020-12-04
|  |  |  | ctc08 | 2020-12-07 | 2020-12-11
|  |  |  | ctc09 | 2020-12-14 | 2020-12-18
|  |  |  | ctc10 | 2020-12-21 | 2020-12-25
|  |  |  | ctc11 | 2020-12-28 | 2020-01-01
|  |  |  | ctc12 | 2020-01-04 | 2020-01-08
build details for upgradation/migration :- |  |  |  | ctc13 | 2020-01-11 | 2020-01-15
|  |  |  | ctc14 | 2020-01-18 | 2020-01-22
oslevel | nim master | build no |  | ctcr | 2020-01-25 | 2020-01-29
72M SP6 | nimitz | latest
72M SP5 | autobella08 | 2016
72M SP4 | autobella08 | 1938
72Q SP3 | nimitz | latest | Note :-
72Q SP2 | autobella08 | 2028 |  | for migration installation use pull installation method instead of push installation
72Q SP1 | autobella08 | 1939 |  | for upgradation use latest build of 72M/H lpp-source location from nimitz/isstnim01 . You can see such list by using showmount command
71X SP8 | nimitz | 1926B_71X |  | eg:- showmount -e nimitz ¦ grep 72H ¦ grep -i 2018A

## Hardware
Lpars for isst weekly runs from ctc03 onwards :- |  |  |  | vios owners & their responsibility :-
owner | lpar name | cec name |  | power model | cec name | hmc | vios name | vios build | owner | responsibility
sameera | towsp01 | 795-DEMO |  | p7 | 795-demo |  | towv1, towv2 | 3.1.0.50 | asha | cec : firmware upgradation vios : vios installation + lun mapping + sea creation
mahesha | towsp02 | 795-DEMO |  | p8 | brit |  | britvios1, britvios2 | 3.1.1.30 | ravi teja
ravi teja | towsp03 | 795-DEMO |  | p9 | nimbus |  | nimbusv1, nimbusv2 | 3.1.1.30 | mahesha
ravi teja | towsp04 | 795-DEMO
ravi g | britsp01 | brit
vandana | britsp02 | brit
sameera | britsp03 | brit
rajesh s | britsp04 | brit
konda | britsp05 | brit
konda | nimbusauto01 | nimbus |  |  | NOTE :- For defect verification use the lpars in your name from either of the list.
mahesha | nimbusauto02 | nimbus
sreejit | nimbusauto03 | nimbus
rajesh s | nimbusauto05 | nimbus
konda | nimbusauto04 | nimbus
Lpars for FV Jobs in jenkins from ctc-2w-02 onwards :- (try to have public ip for your lpars )
owner | 795-demo | brit | p9
apoorva (base) | towsp06 | britsp06, 07 | nimbussp06
asha | towsp07 | britsp08 | -
vidya | - | britsp20,21,22,23 | nimbussp22
ravi teja | towsp08, 09 | britsp09, 10 | -
sameera | - | - | nimbussp14, nimbussp15
mahesha | - | britsp24, britsp25 | -
konda | - | - | nimbussp08, nimbussp09, nimbussp10
rajesh s | - | britsp11,12,13 | -
ravi g | towsp10,11,12 | - | nimbussp11, nimbussp12, nimbussp13
vandana | - | britsp14,15,16 | nimbussp19, nimbussp20, nimbussp21
sreejit | - | britsp17,18,19 | nimbussp16, nimbussp17, nimbussp18
hari | - | - | nimbussp07
Note on C31: Sreejit Nair: ravi has to inform sreejit before taking brit lpars in ctr iteration

## FV automated ters
area | owner | iteration | start date | end date | power model | lpar name | hmc | ter no | oslevel | installation type | tests or jobs to execute | mention jenkins build no
base-nim | ravi teja | ctc-2w-05 | 2020-12-14 | 2020-12-25 | p8 | britsp09, britsp10 |  | 218140 | 72Q | upgradation from 72Q SP2 | AIX_FVTR_FVINSTALL AIX_FVTR_BOSINST_altinst_test fvaso
base-nim | ravi teja | ctc-2w-02 | 2020-11-02 | 2020-11-13 | p7 | towsp08, towsp09 |  | 218129 | 72M | fresh | AIX_FVTR_FVINSTALL AIX_FVTR_BOSINST_altinst_test
base-nim | ravi teja | ctc-2w-03 | 2020-11-16 | 2020-11-27 | p7 | towsp08, towsp09 |  | 218139 | 72Q | migration from 71X SP8 | AIX_FVTR_BOSINST_Installation AIX_FVTR_BOSINST_Migration_Test dst manual test execution
base-nim | ravi teja | ctc-2w-04 | 2020-11-30 | 2020-12-11 | p8 | britsp09, britsp10 |  | 218130 | 72M | migration from 71X SP8 | AIX_FVTR_BOSINST_Installation AIX_FVTR_BOSINST_Migration_Test
base-perf | apoorva | ctc-2w-04 | 2020-11-30 | 2020-12-11 | P8 | britsp07 |  | 218372 | 72Q | fresh | PTX_libpmapi_ASO PTX_libpmapi_1 dst manual test execution
base-perf | apoorva | ctc-2w-03 | 2020-11-16 | 2020-11-27 | p7 | towsp06 |  | 218371 | 72Q | migration from 71X SP8 | AIX_FVTR_LOCAL AIX_FVTR_RAS_SANDBOX dst manual test execution
base-perf | apoorva | ctc-2w-02 | 2020-11-02 | 2020-11-13 | p8 | britsp07 |  | 218370 | 72Q | fresh | PTX_STAT_TOOLS PTX_SVMON
base-perf | apoorva | ctc-2w-05 | 2020-12-14 | 2020-01-22 | p8 | britsp07 |  | 218373 | 72M | upgradation from 72M SP4 | PTX_libpmapi_ASO PTX_libpmapi_1 bos_misc_kernel.g.1
base | asha | ctc-2w-03 | 2020-11-16 | 2020-11-27 | p8 | britsp08 |  | 218177 | 72Q | fresh | bos.p.1 bos_misc.g.1 AIX_FVTR_FVVMM_STAF_SRAD dst manual test execution
base-perf | apoorva | ctc-2w-06 | 2020-12-28 | 2020-12-25 | p7 | towsp06 |  | 218374 | 72M | migration from 71X SP8 | AIX_FVTR_LOCAL AIX_FVTR_RAS_SANDBOX fvaso
base-perf | apoorva | ctc-2w-07 | 2020-01-11 | 2020-01-08 | p9 | nimbussp06 |  | 218375 | 72M | upgradation from 72M SP5 | PTX_STAT_TOOLS PTX_SVMON dst manual test execution
base | vidya | ctc-2w-07 | 2020-01-11 | 2020-01-22 | p8 | britsp20 |  | 218168 | 72M | fresh | bos.p.1 bos_misc.g.1 dst manual test bucket execution
base | vidya | ctc-2w-03 | 2020-11-16 | 2020-11-27 | p9 | nimbussp22 |  | 218165 | 72M | fresh | AIX_FVTR_FVKERNEL_LOADER AIX_FVTR_FVKERNEL_NUMA bos.p.1
base | asha | ctc-2w-02 | 2020-11-02 | 2020-11-13 | p8 | britsp08 |  | 218162 | 72M | fresh | AIX_FVTR_FVKERNEL_PTHREAD_mini AIX_FVTR_FVKERNEL_PTHREAD_new bos_shell.g.1
base | asha | ctc-2w-04 | 2020-11-30 | 2020-12-11 | p8 | britsp08 |  | 218163 | 72M | migration from 71X SP8 | AIX_FVTR_FVKERNEL_FVCMD_new AIX_FVTR_FVKERNEL_PROCFS_AUTO break.p.1
base | vidya | ctc-2w-04 | 2020-11-30 | 2020-12-11 | p9 | nimbussp22 |  | 218171 | 72M | upgradation from 72M SP4 | AIX_FVTR_FVVMM_TET_STAF AIX_FVTR_WLM bos_misc_kernel.g.1
base | vidya | ctc-2w-05 | 2020-12-14 | 2020-12-25 | p9 | nimbussp22 |  | 218166 | 72M | upgradation from 72M SP5 | AIX_FVTR_FVVMM_STAF_36V dst manual test execution AIX_FVTR_FVVMM_STAF_AME_AMS
base | vidya | ctc-2w-06 | 2020-12-28 | 2020-01-08 | p8 | britsp20 |  | 218167 | 72M | fresh | AIX_FVTR_FVVMM_STAF_SRAD AIX_FVTR_FVVMM_STAF_16GB bos_misc.g.1
base | asha | ctc-2w-05 | 2020-12-14 | 2020-12-25 | p8 | britsp08 |  | 218164 | 72M | upgradation from 72M SP4 | AIX_FVTR_LIBC_STAF dst manual test execution AIX_FVTR_LIBC_TET
base | vidya | ctc-2w-04 | 2020-11-30 | 2020-12-11 | p8 | britsp20 |  | 218170 | 72M | migration from 71X SP8 | AIX_FVTR_DBX_CT dst manual test execution AIX_FVTR_COMMANDS_CVK
base | vidya | ctc-2w-02 | 2020-11-02 | 2020-11-13 | p8 | britsp20 |  | 218169 | 72M | fresh | AIX_FVTR_COMMANDS_CMDKSH93 AIX_FVTR_COMMANDS_STAF dst manual test bucket execution
base | apoorva | ctc-2w-05 | 2020-12-14 | 2020-12-25 | p7 | towsp06 |  | 218175 | 72Q | upgradation from 72Q SP2 | AIX_FVTR_FVKERNEL_LOADER AIX_FVTR_FVKERNEL_NUMA bos.p.1 dst manual test bucket execution
base | asha | ctc-2w-06 | 2020-12-28 | 2020-01-08 | p8 | britsp08 |  | 218179 | 72Q | upgradation from 72Q SP1 | AIX_FVTR_FVKERNEL_PTHREAD_mini AIX_FVTR_FVKERNEL_PTHREAD_new AIX_FVTR_FVVMM_STAF_16GB
base | vidya | ctcr01 | 2020-01-25 | 2020-01-29 | p8 | britsp20 |  | 218181 | 72Q | fresh | bos.p.1 bos_misc.g.1
base | asha | ctc-2w-07 | 2020-01-11 | 2020-01-22 | p8 | britsp08 |  | 218180 | 72Q | fresh | AIX_FVTR_FVKERNEL_FVCMD_new AIX_FVTR_FVKERNEL_PROCFS_AUTO break.p.1
base | apoorva | ctc-2w-04 | 2020-11-30 | 2020-12-11 | p8 | britsp06 |  | 218174 | 72Q | fresh | AIX_FVTR_FVVMM_TET_STAF AIX_FVTR_WLM bos_misc.g.1
base | apoorva | ctc-2w-06 | 2020-12-28 | 2020-01-08 | p9 | nimbussp06 |  | 218176 | 72Q | migration from 71X SP8 | AIX_FVTR_FVVMM_STAF_36V AIX_FVTR_FVVMM_STAF_AME_AMS AIX_FVTR_COMMANDS_CVK
base | asha | ctc-2w-04 | 2020-11-30 | 2020-12-11 | p7 | towsp07 |  | 218178 | 72Q | upgradation from 72Q SP2 | AIX_FVTR_LIBC_STAF AIX_FVTR_LIBC_TET bos_shell.g.1
base | apoorva | ctc-2w-02 | 2020-11-02 | 2020-11-13 | p8 | britsp06 |  | 218172 | 72Q | fresh | dst manual test bucket execution bos_misc.g.1 AIX_FVTR_DBX_CT
base | apoorva | ctc-2w-03 | 2020-11-16 | 2020-11-27 | p9 | nimbussp06 |  | 218173 | 72Q | upgradation from 72Q SP1 | AIX_FVTR_COMMANDS_CMDKSH93 AIX_FVTR_COMMANDS_STAF bos_misc_kernel.g.1
commo-tcp | sreejit | ctc-2w-02 | 2020-11-02 | 2020-11-13 | p9 | nimbussp16, nimbussp17, nimbussp18 |  | 218187 | 72M | upgradation from 72M SP4 | AIX_FVTR_TCPIP_P4 AIX_FVTR_TCPIP_P1
commo-tcp | vandana | ctc-2w-02 | 2020-11-02 | 2020-11-13 | p8 | britsp14, britsp15, britsp16 |  | 218194 | 72Q | fresh | AIX_FVTR_TCPIP_P3 AIX_FVTR_TCPIP_P1
commo-tcp | sreejit | ctc-2w-04 | 2020-11-30 | 2020-12-11 | p9 | nimbussp16, nimbussp17, nimbussp18 |  | 218189 | 72M | fresh | AIX_FVTR_TCPIP_P2_CT AIX_FVTR_TCPIP_P3
commo-tcp | vandana | ctc-2w-03 | 2020-11-16 | 2020-11-27 | p9 | nimbussp19, nimbussp20, nimbussp21 |  | 218195 | 72Q | migration from 71X SP8 | AIX_FVTR_TCPIP_P2_CT AIX_FVTR_TCPIP_P1_CT
commo-tcp | sreejit | ctc-2w-07 | 2020-01-11 | 2020-01-22 | p8 | britsp17, britsp18, britsp19 |  | 218192 | 72M | migration from 71X SP8 | AIX_FVTR_TCPIP_P3_CT AIX_FVTR_TCPIP_P1_CT
commo-tcp | vandana | ctc-2w-04 | 2020-11-30 | 2020-12-11 | p8 | britsp14, britsp15, britsp16 |  | 218196 | 72Q | fresh | AIX_FVTR_TCPIP_P4 AIX_FVTR_TCPIP_LI_1BC
commo-tcp | sreejit | ctc-2w-03 | 2020-11-16 | 2020-11-27 | p9 | nimbussp16, nimbussp17, nimbussp18 |  | 218188 | 72M | fresh | AIX_FVTR_TCPIP_LI_2JQ AIX_FVTR_TCPIP_LI_1BC
commo-tcp | ravi g | ctc-2w-02 | 2020-11-02 | 2020-11-13 | p7 | towsp10, towsp11, towsp12 |  | 218184 | 72M | fresh | AIX_FVTR_TCPIP_P1 AIX_FVTR_TCPIP_P2
commo-tcp | ravi g | ctc-2w-04 | 2020-11-30 | 2020-12-11 | p9 | nimbussp11, nimbussp12, nimbussp13 |  | 218292 | 72Q | fresh | ndd for halekala AIX_FVTR_TCPIP_LI_2JQ | need to open lab ticket for 1-1 or back to back adapter connection
commo-tcp | ravi g | ctc-2w-03 | 2020-11-16 | 2020-11-27 | p9 | nimbussp11, nimbussp12, nimbussp13 |  | 218291 | 72Q | migration from 71X SP8 | ndd for austin AIX_FVTR_TCPIP_P2_CT
io | mahesha | ctc-2w-03 | 2020-11-16 | 2020-11-27 | p8 | britsp24, britsp25 |  | 218200 | 72Q | upgradation from 72Q SP1 | AIX_FVTR_FVFS AIX_FVTR_FVFS_fvfs
io | mahesha | ctc-2w-06 | 2020-12-28 | 2020-01-08 | p8 | britsp24, britsp25 |  | 218202 | 72Q | upgradation from 72Q SP2 | AIX_FVTR_FVFS_fvcmdfs AIX_FVTR_FVFS_fvsysxaio
io | mahesha | ctc-2w-04 | 2020-11-30 | 2020-12-11 | p8 | britsp24, britsp25 |  | 218201 | 72Q | migration from 71X SP8 | AIX_FVTR_LVM_changevg AIX_FVTR_LVM_CLVM
io | sameera | ctc-2w-05 | 2020-12-14 | 2020-12-25 | p9 | nimbussp14, nimbussp15 |  | 218207 | 72M | fresh | AIX_FVTR_FVFS AIX_FVTR_FVFS_fvfs
io | sameera | ctc-2w-02 | 2020-11-02 | 2020-11-13 | p9 | nimbussp14, nimbussp15 |  | 218204 | 72M | upgradation from 72M SP4 | AIX_FVTR_FVFS_fvsysxaio AIX_FVTR_FVFS_fvsysj2
io | sameera | ctc-2w-04 | 2020-11-30 | 2020-12-11 | p9 | nimbussp14, nimbussp15 |  | 218206 | 72M | migration from 71X SP8 | AIX_FVTR_FVFS_fvcmdfs AIX_FVTR_FVFS_fvsyslfs
io | sameera | ctc-2w-03 | 2020-11-16 | 2020-11-27 | p9 | nimbussp14, nimbussp15 |  | 218205 | 72M | upgradation from 72M SP5 | AIX_FVTR_LVM_CLVM AIX_FVTR_LVM_NON_CLVM
caa | vidya | ctc-2w-06 | 2020-12-28 | 2020-01-08 | p8 | britsp20, britsp21, britsp22, britsp23 |  | 218182 | 72Q | fresh | CAA
caa | vidya | ctc-2w-05 | 2020-12-14 | 2020-12-25 | p8 | britsp20, britsp21, britsp22, britsp23 |  | 218183 | 72M | fresh | CAA
commo-nfs | konda | ctc-2w-03 | 2020-11-16 | 2020-11-27 | p9 | nimbussp08, nimbussp09, nimbussp10 |  | 218040 | 72M | migration from 71X SP8 | nfsfunct.p.1 nfs_remount.p.1 nfsaudit.p.1
commo-nfs | konda | ctc-2w-05 | 2020-12-14 | 2020-12-25 | p9 | nimbussp08, nimbussp09, nimbussp10 |  | 218042 | 72M | upgradation from 72M SP5 | replica_nfs.p.1 edge_cache.p.1 nfsstress.p.1
commo-nfs | konda | ctc-2w-04 | 2020-11-30 | 2020-12-11 | p9 | nimbussp08, nimbussp09, nimbussp10 |  | 218038 | 72M | upgradation from 72M SP4 | nfs1tb.p.1 nis_fvnfs.p.1 nis.p.1 autofs.p.1
commo-nfs | rajesh s | ctc-2w-03 | 2020-11-16 | 2020-11-27 | p8 | britsp11, britsp12, britsp13 |  | 218041 | 72Q | fresh | nfs_remount.p.1 nfsaudit.p.1 nfsstress.p.1
commo-nfs | rajesh s | ctc-2w-05 | 2020-12-14 | 2020-12-25 | p8 | britsp11, britsp12, britsp13 |  | 218043 | 72Q | migration from 71X SP8 | replica_nfs.p.1 edge_cache.p.1 nfsfunct.p.1
commo-nfs | rajesh s | ctc-2w-04 | 2020-11-30 | 2020-12-11 | p8 | britsp11, britsp12, britsp13 |  | 218039 | 72Q | upgradation from 72Q SP1 | nfs1tb.p.1 nis_fvnfs.p.1 nis.p.1 autofs.p.1
commo-tcp | vandana | ctc-2w-05 | 2020-12-14 | 2020-12-25 | p9 | nimbussp19, nimbussp20, nimbussp21 |  | 218197 | 72Q | upgradation from 72Q SP2 | AIX_FVTR_TCPIP_P4_CT AIX_FVTR_TCPIP_P2
commo-tcp | sreejit | ctc-2w-06 | 2020-12-28 | 2020-01-08 | p8 | britsp17, britsp18, britsp19 |  | 218191 | 72M | upgradation from 72M SP5 | AIX_FVTR_TCPIP_P4 AIX_FVTR_TCPIP_P2
commo-tcp | sreejit | ctc-2w-05 | 2020-12-14 | 2020-12-25 | p9 | nimbussp16, nimbussp17, nimbussp18 |  | 218190 | 72M | fresh | AIX_FVTR_TCPIP_P4 AIX_FVTR_TCPIP_P4_CT
commo-tcp | ravi g | ctc-2w-05 | 2020-12-14 | 2020-12-25 | p9 | nimbussp11, nimbussp12, nimbussp13 |  | 218185 | 72M | fresh | ndd for houston AIX_FVTR_TCPIP_P3_CT | need to open lab ticket for 1-1 or back to back adapter connection
commo-tcp | ravi g | ctc-2w-06 | 2020-12-28 | 2020-01-08 | p9 | nimbussp11, nimbussp12, nimbussp13 |  | 218186 | 72M | fresh | ndd for shiner AIX_FVTR_TCPIP_P1_CT
commo-tcp | vandana | ctc-2w-06 | 2020-12-28 | 2020-01-08 | p9 | nimbussp19, nimbussp20, nimbussp21 |  | 218198 | 72Q | upgradation from 72Q SP1 | ndd for houston AIX_FVTR_TCPIP_P1
io | sameera | ctc-2w-06 | 2020-12-28 | 2020-01-08 | p9 | nimbussp14, nimbussp15 |  | 218208 | 72M | fresh | AIX_FVTR_LVM_changevg AIX_FVTR_FVFS_fvsysxaio
io | mahesha | ctc-2w-02 | 2020-11-02 | 2020-11-13 | p8 | britsp24, britsp25 |  | 218199 | 72Q | fresh | AIX_FVTR_FVFS_fvsysj2 AIX_FVTR_FVFS_fvsyslfs
io | mahesha | ctc-2w-07 | 2020-01-11 | 2020-01-22 | p8 | britsp24, britsp25 |  | 218203 | 72Q | fresh | AIX_FVTR_FVFS_fvfs AIX_FVTR_LVM_NON_CLVM
commo-tcp | vandana | ctcr01 | 2020-01-25 | 2020-01-29 | p9 | nimbussp19, nimbussp20, nimbussp21 |  | 218193 | 72M | fresh | AIX_FVTR_TCPIP_P1
commo-tcp | ravi g | ctcr01 | 2020-01-25 | 2020-01-29 | p8 | britsp17, britsp18, britsp19 |  | 218290 | 72Q | fresh | AIX_FVTR_TCPIP_P3
base-nim | hari | ctc-2w-04 | 2020-11-30 | 2020-12-11 | p9 | nimbussp07 |  | 218268 | 72M | fresh | cd | need to open lab ticket for device
base-nim | hari | ctc-2w-04 | 2020-11-30 | 2020-12-11 | p9 | nimbussp07 |  | 218269 | 72Q | fresh | dvd
base-nim | hari | ctc-2w-05 | 2020-12-14 | 2020-12-25 | p9 | nimbussp07 |  | 218270 | 72M | migration from 71X SP8 | dvd
base-nim | hari | ctc-2w-05 | 2020-12-14 | 2020-12-25 | p9 | nimbussp07 |  | 218271 | 72Q | upgradation from 72Q SP1 | cd
base-nim | hari | ctc-2w-06 | 2020-12-28 | 2020-01-08 | p9 | nimbussp07 |  | 218272 | 72M | upgradation from 72M SP5 | flash device
base-nim | hari | ctc-2w-06 | 2020-12-28 | 2020-01-08 | p9 | nimbussp07 |  | 218273 | 72Q | migration from 71X SP8 | rdx
base-nim | hari | ctc-2w-07 | 2020-01-11 | 2020-01-22 | p9 | nimbussp07 |  | 218274 | 72M | upgradation from 72M SP4 | rdx
base-nim | hari | ctc-2w-07 | 2020-01-11 | 2020-01-22 | p9 | nimbussp07 |  | 218275 | 72Q | upgradation from 72Q SP2 | flash device
Note on I6: Sreejit Nair: deleter ter no :- 218149
Note on I7: Sreejit Nair: deleter ter no :- 218148
Note on I8: Sreejit Nair: deleter ter no :- 218147
Note on I9: Sreejit Nair: deleter ter no :- 218156
Note on I11: Sreejit Nair: deleter ter no :- 218155
Note on I12: Sreejit Nair: deleter ter no :- 218154
Note on G67: Sreejit Nair: ravi has to inform sreejit before taking these lpar

## manual ters
area | component | owner | oslevel | iteration | start date | end date | ter no | defect no.
commo | tcp | ravi g | 72M | ctc-2w-03 | 2020-11-16 | 2020-11-27 | 218228 | 1099193, 1103198, 1105030, 1103198
commo | tcp | vandana | 72Q | ctc-2w-03 | 2020-11-16 | 2020-11-27 | 218229 | 1099193, 1103198, 1105030,1103198
commo | tcp | ravi g | 72M | ctc-2w-02 | 2020-11-02 | 2020-11-13 | 218226 | 1102684, 1111718, 1101210
commo | tcp | vandana | 72Q | ctc-2w-02 | 2020-11-02 | 2020-11-13 | 218227 | 1102684, 1111718, 1101210
base | base | vidya | 72Q | ctc-2w-04 | 2020-11-30 | 2020-12-11 | 218235 | 1101486, 1104640, 1110861, 1112155
base | base | asha | 72Q | ctc-2w-02 | 2020-11-02 | 2020-11-13 | 218233 | 1116973, 1104527, 1109487
base | base | apoorva | 72M | ctc-2w-02 | 2020-11-02 | 2020-11-13 | 218230 | 1101486, 1104640, 1110861
base | base | asha | 72M | ctc-2w-03 | 2020-11-16 | 2020-11-27 | 218231 | 1116973, 1104527, 1109487
base | nim | ravi teja | 72M | ctc-2w-04 | 2020-11-30 | 2020-12-11 | 218232 | 1105038, 1115690, 1111257,
base | nim | sameera | 72Q | ctc-2w-03 | 2020-11-16 | 2020-11-27 | 218234 | 1114173, 1102545, 1108959
base | nim | sameera | 72M | ctc-2w-04 | 2020-11-30 | 2020-12-11 | 218221 | apply-reject 1 ptf at a time
base | nim | ravi teja | 72Q | ctc-2w-04 | 2020-11-30 | 2020-12-11 | 218220 | apply-reject 1 ptf at a time
base | nim | sameera | 72M | ctc-2w-06 | 2020-12-28 | 2020-01-08 | 218224 | backup restore on tape | need to open lab ticket to move tape & dvd to either of the available cec :-
base | nim | sameera | 72M | ctc-2w-05 | 2020-12-14 | 2020-12-25 | 218222 | backup restore on dvd
base | nim | ravi teja | 72Q | ctc-2w-06 | 2020-12-28 | 2020-01-08 | 218223 | backup restore on dvd
base | nim | ravi teja | 72Q | ctc-2w-05 | 2020-12-14 | 2020-12-25 | 218225 | backup restore on tape
io | fs | apoorva | 72Q | ctc-2w-04 | 2020-11-30 | 2020-12-11 | 218462 | 1112120
base | nim | sameera | 72Q | ctc-2w-04 | 2020-11-30 | 2020-12-11 | 218465 | 1105038, 1115690, 1111257,
base | base | asha | 72M | ctc-2w-05 | 2020-12-14 | 2020-12-25 | 218463 | 1115635, 1101318, 1100564
base | base | vidya | 72Q | ctc-2w-05 | 2020-11-30 | 2020-12-11 | 218467 | 1115635, 1101318, 1100564
base | nim | ravi teja | 72M | ctc-2w-05 | 2020-12-14 | 2020-12-25 | 218464 | 1105531, 1109076
base | nim | sameera | 72Q | ctc-2w-05 | 2020-12-14 | 2020-12-25 | 218466 | 1105531, 1109076

## ISST weekly automated ters
owner | testcase name | iteration | start day | end day | level | lpar name | cec name | power model | hmc
ravi g | Weekly Automated Base I/O NFS TCP TCP_SERVER | ctc03-ctc14 | Monday | Friday | 72M | britsp01 | brit | p8
konda | Weekly Automated Base I/O NFS TCP TCP_SERVER | ctc03-ctc14 | Monday | Friday | 72Q | nimbusauto01 | nimbus | p9
mahesha | Weekly Automated Base I/O NFS TCP | ctc03-ctc14 | Monday | Friday | 72Q | nimbusauto02 | nimbus | p9
vandana | Weekly Automated Base I/O NFS TCP | ctc03-ctc14 | Monday | Friday | 72M | britsp02 | brit | p8
sameera | Weekly Automated Base I/O NFS TCP Probevue | ctc03-ctc14 | Monday | Friday | 72Q | britsp03 | brit | p8
sreejit | Weekly Automated Base I/O NFS TCP Probevue | ctc03-ctc14 | Monday | Friday | 72M | nimbusauto03 | nimbus | p9
rajesh s | Weekly Automated Base I/O NFS NFS_SERVER TCP | ctc03-ctc14 | Monday | Friday | 72Q | britsp04 | brit | p8
rajesh s | Weekly Automated Base I/O NFS NFS_SERVER TCP | ctc03-ctc14 | Monday | Friday | 72M | nimbusauto05 | nimbus | p9
konda | Weekly Automated Base I/O NFS NFS_SERVER TCP TCP_SERVER | ctc03-ctc14 | Monday | Friday | 72M | nimbusauto04 | nimbus | p9
konda | Weekly Automated Base I/O NFS NFS_SERVER TCP TCP_SERVER | ctc03-ctc14 | Monday | Friday | 72Q | britsp05 | brit | p8
sameera | Weekly Automated I/O | ctc03-ctc14 | Monday | Friday | 72Q | towsp01 | 795-demo | p7
mahesha | Weekly Automated I/O | ctc03-ctc14 | Monday | Friday | 72M | towsp02 | 795-demo | p7
ravi teja | Weekly Automated Base | ctc03-ctc14 | Monday | Friday | 72M | towsp03 | 795-demo | p7
ravi teja | Weekly Automated Base | ctc03-ctc14 | Monday | Friday | 72Q | towsp04 | 795-demo | p7
Note:- | Niranjan will trigger these jobs from CT tool from ctc04 onwards
it’s a isst weekly ter which needs to be executed & finished in 1 week. It will be repeated every week